## Effort Estimation
Issue # | Summary of Tasks | Estimate (mins) | Non-coding Effort (mins) | Coding Effort (mins) | Estimator | Implementors
33 | Add real user data | 30 | 0 | 60 | Peter Law | Peter Law
34 | Execute Stakeholder Tests | 75 | 30 | 60 | Peter Law | Peter Law
36 | Update .io page | 30 | 0 | 30 | Peter Law | Peter Law
39 | Fix ESLint Errors | 60 | 60 | 60 | Peter Law | Peter Law
45 | Remove the stuff remaining in the Stuff category | 15 | 0 | 12 | Denny Huang | Denny Huang
51 | hawaii.edu account signups only | 30 | 12 | 18 | Denny Huang | Denny Huang
31 | Finish Contact page | 120 | 60 | 60 | Denny Huang | Denny Huang
32 | Implement FAQs | 90 | 30 | 60 | Denny Huang | Denny Huang
43 | Resolve button misdirections | 25.2 | 0 | 25.2 | Denny Huang | Denny Huang
29 | Implement matching algorithm | 210 | 30 | 180 | Christian Komo | Christian Komo
44 | Add Admin pages | 90 | 0 | 90 | Christian Komo | Christian Komo
35 | Implement acceptance testing | 60 | 12 | 48 | Thomas Chen | Thomas Chen
30 | Implement messaging feature | 120 | 30 | 90 | Thomas Chen | Thomas Chen
29 | Implement edit profile page | 120 | 30 | 90 | Christian Komo | Christian Komo
26 | Create student Prisma model | 30 | 15 | 15 | Christian Komo | Christian Komo
17 | Implement create student page | 240 | 45 | 195 | Christian Komo | Christian Komo
10 | Create and embed mockup pages | 120 | 120 | 0 | Christian Komo | Christian Komo

## Development Experience
Team Member | Software Development Experience (months) | How was coding effort tracked? | How was non-coding effort tracked?
Denny Huang | 12 | Best Guess | Best Guess
Peter Law | 48 | Best Guess | Best Guess
Christian Komo | 18 | Best guess | Best guess
Thomas Chen | 20 | Best guess | Best Guess